## Product Backlog
ID | User Story
16 | As a student, I must be able to view my personal schedule.
78 | As a staff member, I must be able to view proctoring schedules
102 | As a staff member, I must be able to view my schedule
84 | As a staff member, I must be able to view all courses I teach.
103 | As a staff member, I should be able to view staff, group and course schedules
88 | As a staff member, I must be able to view associated student schedules
89 | As a staff member, I should be able to view schedule of other staff within department
7 | As a student, I must be able to view my attendance.
72 | As a TA, I should enter and modify student attendance
13 | As a student, I must be able to view transcript within my years study.
87 | As a staff member, I must be able to enter students' grades
12 | As a student, I should be able to access course work grades of previous semesters.
11 | As a student, I must be able to view grades of quizzes, assignments, midterms, finals and projects of my current semester courses
19 | As a student, I must be able to view my exam schedule and exam seats.
57 | As a professor/lecturer, I must be able to define evaluations for my courses.
58 | As a professor/lecturer, I must be able to specify the grades distribution for my courses.
59 | As a professor/lecturer, I must set dates and deadlines for my evaluations.
60 | As a professor/lecturer, I must be able to view grade statistics for my courses
61 | As a professor/lecturer, I must be able to upload course material.
23 | As a student, I must be able to view course information, announcements and material.
132 | As a system user, I should be able to download course material
41 | As a student, I must be able to submit projects and assignments online.
50 | As a bachelor student, I must be able to upload thesis
51 | As a bachelor student, I must be able to keep track of my progress and view my evalution grades posted by my supervisor.
39 | As a student, I must be able to request bachelor thesis topics (including topics abroad)
52 | As a graduate student, I must be able to view the offered Masters/PhD programs.
53 | As a graduate student, I should be able to post research supervision requests
54 | As a graduate student, I must be able to submitt progress reports
55 | As a graduate student, I should be able to view all of my submitted progress reports.
66 | As a professor/lecturer, I should be able to post research supervision opportunities for my students.
67 | As a professor/lecturer, I must be able to view a list of bachelor that I am supervising, along with their info
68 | As a professor/lecturer, I should be able to post thesis evaluation for bachelor/ graduate students that I am supervising.
69 | As a professor/lecturer, I must be able to to list the Master and PhD students under my supervision
70 | As a professor/lecturer, I should be able to to check status of graduate students (in progress, done, …)
18 | As a student, I should be able to advertise from which and to which tutorial I would like to switch, submit switching requests, and respond to them
80 | As a staff member, I should be able to send recommendations for my teaching schedule
79 | As a staff member, I should advertise for proctoring switching
82 | As a staff member, I must be able to schedule compensation slot with the option of selecting multiple groups
10 | As a student, I must be able to add and drop courses.
49 | As an advising student, I must be able to to select the courses that I will be taking this semester
20 | As a student, I must be able to view my bus schedule and daily timing of busses.
21 | As a student, I should be able to reserve a bus at the beginning of the academic year
22 | As a student, I must be able to view staff information for registered courses .
9 | As a student, I should be able to view course prerequisites
24 | As a student, I should be able to access previous semesters materials
65 | As a professor/lecturer, I should be able to reserve a meeting room online
71 | As a staff member, I should view the number of hours spent and the number of hours remaining to be spent
74 | As a TA, I should be able to open and close the tutorial sessions so the system can record the amount of time spent by the TA teaching that specific slot.
29 | As a student, I must be able to request remarking online.
30 | As a student, I must be able to be view the status of remarking
32 | As a student, I must be able to request makeup and improvement online
33 | As a student, I must be able to view remaining free makeups
34 | As a student, I must be able to check my financial balance
35 | As a student, I should be able to pay my fees and any other expenses online
6 | As a student, I must be able to declare my major.
25 | As a student, I must be able to evaluate staff anonymously throughout the semester.
26 | As a student, I must be able to evaluate courses anonymously throughout the semester.
42 | As a student, I must be able to reserve office hours online.
112 | As a system user, I could report an issue to IT department
63 | As a professor/lecturer, I should be able to post offered junior TA programs
14 | As a student, I should be able to export transcript into printable format (in both GPA scales)
17 | As a student, I should be able to export personal schedule in a printable format
37 | As a student, I should be able to request permission for after-hours stay.
81 | As a system user, I must be able to view students' profile pages (including emails and IDs for staff members only)
93 | As a staff member, I should be able to set up reminders for upcoming meetings
96 | As a staff member, I must be able to search the grades of my students.
104 | As a system user, I must be able to view my calendar (academic and upcoming university events)
113 | As a system user, I could reserve different sports fields online
15 | As a student, I should be able to access my personal student ranking.
45 | As a student, I should be able to view offered JTA programs
46 | As a student, I should be able to submit JTA application online.
47 | As a student, I should be able to view internship opportunites and bookmark those that interest me
48 | As a student, I should be able to view finished internships (accepted and rejected ones by scad with justifcations for rejections and remaining hours to graduate
27 | As a student, I should be able to convert my GPA from 5-0.7 to 0-4.0 scaler.
28 | As a student, I should be able to calculate my GPA.
108 | As a system user, I should be able to browse through library books
133 | As a system user, I should be able to renew borrowing period
NOTES
DURATION OF EACH SPRINT IS 10 DAYS
ESTIMATED TIME FOR PROJECT COMPLETION IS 42 DAYS
Color "YELLOW" is Sprint 1
Color "BLUE" is Sprint 2
Color "RED" is Sprint 3
Color "GREEN" is Sprint 4

## Sprint 1 Backlog
ID | User Story | Team members | Story Points | Reasons | notes for UX
78 | view proctoring schedules | Ali | 2 | Only one type of schedule and it does not have many details or variances
102 | View my schedule | Mayar | 2 | Only one type of schedule
84 | Display my courses' schedules | Saeed | 2 | Only one type of schedule | Automatically display assigned courses to student , when student selects the course schedule to the course
89 | Filter staff members by course or semester or search by name or id to view their schedules | Saeed | 1 | In the UX, only a search bar is needed. Testing is also fairly easy
103 | View staff, group and course schedules | Ali | 8 | Different types of schedules to be handled differently
88 | Filter students by course or semester or search by name or id to view their schedules | Hussein | 1 | In the UX, only a search bar is needed. Testing is also fairly easy
89 | Display a list of the staff members within my department | Mayar | 1 | We are just displaying a single list based on the user
7 | Display student attendance | Hussein | 2 | A lot of information will be displayed (ex. tutorial session, names and id of students and whether they are present or absent)
72 | Edit and modify a specific student's attendance in a specific tutorial | Salma | 4 | In the UX, it requires selecting a tutorial number, session date, selecting a student and modifying attendance (multiple steps in the UX). In the testing, we need to test from the student side and the TA side
13 | Display years of study of student to view this year's transcript | Mahmoud | 1 | It's a simple task that only requires displaying dates
13 | Display student transcript for selected years of study | ali | 2 | A simple static display but with many details
12 | Display list of all previous semesters for student | Salma | 1 | Displaying a list is a simple task
12 | For a selected semester, display a list of courses taken | saeed | 1 | Displaying a list is a simple task
12 | Access and display course work grades of a course taken in previous semester | mayar | 2 | A simple static display but with many details
87 | Selecting a course to grade | Hussein | 1 | Selecting is a simple task
87 | Selecting a course to view its assessments | Hussein | 1 | Selecting is a simple task
87 | Select an assessment to grade | Mahmoud | 1 | Selecting is a simple task
87 | Entering the grades for the students or groups of students | Mahmoud | 4 | In the UX, it requires multiple steps in the UX to filter and select what we want to grade. In the testing, we need to test from the student side and the TA side
11 | Display grades of quizzes, assignments, midterms, finals and projects of student's current semester courses | Saeed | 2 | A simple static display but with many details
19 | Display exam schedule | Mahmoud | 2 | Only one type of schedule
57 | Defining coursework assessments and evaluations | Saeed | 4 | Requires a lot of testing to verify the functionality
58 | Defining grade distribution and specifying weight for each assessment type | Ali | 4 | Requires lots of testing to verify that it is fully functioning (entering valid data, total adds to 100, etc.)
59 | Set dates and deadlines for assessments | Salma | 2 | Assigning a single date value to a selected assessment
60 | Display grade statistics of course | Ali | 8 | Complex display with many calculations and data presentation is important

## Sprint 2 Backlog
ID | User Story | Team Member
61 | Upload course material | Mayar
23 | Display the course's info | Ali
23 | View the latest material used for a course | Hussein
132 | Download uploaded course materials | Mayar
41 | Display list of assignments available for submission | Saeed
41 | Select assignment to be submitted | Saeed
41 | Upload assignment/project file | Ali
50 | Upload bachelor thesis | Hussein
51 | Display progress of bachelor student and grades of evaluations | Mahmoud
39 | Display available bachelor thesis topics | Hussein
39 | Submit request for bachelor thesis topic | Salma
39 | Approve or reject a student's bachelor thesis topic | Mahmoud
52 | View Master's & PHD topic | Salma
53 | Requesting a Master's & PHD topic | Ali
54 | Upload progress report | Saeed
55 | View submitted progress report | Mayar
66 | Post a masters or PHD topic | Salma
67 | View bachelor students that a lecturer is currently supervising | Hussein
68 | select a bachelor/graduate student under lecturer's supervision | Mahmoud
68 | Evaluate the selected bachelor/graduate student's thesis/work | Saeed
69 | Display a list of graduate students under the lecturer's supervision | Ali
70 | Check the status of a lecturer's ongoing graduate students | Salma
18 | Create an advertisement from which and to which tutorial a student would like to switch | Hussein
18 | Display all offered switches for the tutorial the student wants to switch to | Hussein
18 | submit a tutorial switch request | Hussein
18 | respond to tutorial switch request | Hussein
80 | Display teaching assistants' courses' schedules so that the Teaching assistants can select slots to associate themselves with | Mahmoud
80 | Select certain slots to teach in | Saeed

## Sprint 3 Backlog
ID | User Story | Team Member | Story points | Reason
79 | Advertisement of assigned proctoring slots and displaying prefered slots | Mahmoud
79 | Switching proctoring slots | Ali
82 | Scheduling compensation for multiple groups | Salma
10 | Add and drop courses. | Mayar
49 | Display available courses to select from | Salma
49 | Select a course to take this semeseter | Mayar
20 | Display bus schedule | Ali
21 | Allow for a student to reserve a bus | Salma
22 | Display the staff member's info | Salma
9 | Display the course's info | Ali
24 | Allow students to access the course material of previous years | Hussein
65 | Display a list of available rooms | Ali
65 | View room schedules and capacities | Mahmoud
65 | Reserve a selected free tutorial room/lecture hall at a given time slot for compensations/revisions | Hussein
65 | Cancel one of the staff's existing reservations | Saeed
71 | view the number of hours spent and the number of hours remaining to be spent for a staff member | Hussein
74 | Calculate and keep track of the duration of the tutorial | Saeed
29 | Display available courses to be remarked | Ali
29 | Select a specific course to be remaked | Salma
30 | View status of a student's current remarkings | Ali
32 | Display available courses from makeup and improvement | Hussein
32 | Request a makeup or improvement for a specific course | Hussein
33 | Display the number of remaining free makeups | Ali
34 | Display financial balance | Saeed
35 | Select installement to pay | Salma
35 | Pay the selected installement | Mayar
6 | Select major | Saeed
25 | Display list of staff to be evaluated | Saeed
25 | Select staff to be evaluated | Mayar
25 | Evaluate a selected staff member | Mahmoud
26 | Display list of courses to be evaluated | Hussein
26 | Select course to be evaluated | Saeed
26 | Evaluate a selected course | Mahmoud

## Sprint 4 Backlog
ID | User Story | Team Member
42 | Display list of a student's staff available for office hours | Mayar
42 | Select a staff for office hours | Salma
42 | Send office hours request | Huessin
112 | Report an issue to the IT department | Saeed
63 | Advertise JTA positions | Saeed
14 | Export selected transcript into printable format (in both GPA scales) | Huessin
17 | Export personal schedule in a printable format | Mayar
37 | Submit request for after hours stay | Salma
81 | Search for a student using their name | Ali
#REF! | Scheduling a post on the forums | Mahmoud
93 | Acessing the deparment's meeting calendar to select a meeting | Salma
93 | Select a meeting to send a reminder to its members | Salma
96 | Select a course from the list of courses to view its students | Huessin
96 | Select a student to view their grades | Huessin
#REF! | Suggesting specific slots to proctor in | Ali
104 | View my calendar | Saeed
113 | Viewing the sport fields page | Mahmoud
15 | Allow a student to access their personal student ranking. | Saeed
45 | Display list of available JTA programs | Salma
46 | Select JTA program | Mayar
46 | Submit JTA request form | Huessin
47 | Display available internships | Mahmoud
47 | Bookmark internship of interest | Mahmoud
48 | Display finished intership along with status | Mayar
27 | Convert GPA to American scale | Ali
28 | Calculate GPA | Ali
108 | Browse through the unversity's library and search through the available books | Saeed
133 | View a list of the books borrowed | Saeed